## Project
Project Overview
Project Name
Project Manager
Description
Start date (read-only) | 2022-02-14
Finish date (read-only) | 2022-06-16
Duration (read-only) | Pro only
Progress (read-only) | 0%
Work (read-only) | Pro only
Cost (read-only) | Pro only

## Tasks
[7 empty] | March |  |  |  |  | April |  |  |  | May |  |  |  | June |  |  |  |  | July |  |  |  | August |  |  |  | September |  |  |  |  | October |  |  |  | November |  |  |  | December |  |  |  |  | January |  |  |  | February |  |  |  | March |  |  |  |  | April |  |  |  | May |  |  |  | June |  |  |  |  | July |  |  |  | August |  |  |  |  | September |  |  |  | October |  |  |  | November
24 | WBS | description | date de début | date de fin |  |  | 28/02/2022 |  |  |  |  | 04/04/2022 |  |  |  | 02/05/2022 |  |  |  | 30/05/2022 |  |  |  |  | 04/07/2022 |  |  |  | 01/08/2022 |  |  |  | 29/08/2022 |  |  |  |  | 03/10/2022 |  |  |  | 31/10/2022 |  |  |  | 28/11/2022 |  |  |  |  | 02/01/2023 |  |  |  | 30/01/2023 |  |  |  | 27/02/2023 |  |  |  |  | 03/04/2023 |  |  |  | 01/05/2023 |  |  |  | 29/05/2023 |  |  |  |  | 03/07/2023 |  |  |  | 31/07/2023 |  |  |  |  | 04/09/2023 |  |  |  | 02/10/2023 |  |  |  | 30/10/2023 |  | 15
[5 empty] | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | Su
1 | 1 | réalisation du graphe sur papier | 2022-02-14 | 2022-02-14 | [16 empty] | ¦
2 | 2 | cahier des charges | 2022-02-14 | 2022-02-28 | [16 empty] | ¦
3 | 3 | Réalisation du WBS | 2022-02-28 | 2022-03-07 | [16 empty] | ¦
4 | 4 | Matrice des responsabilités | 2022-03-07 | 2022-03-07 | [16 empty] | ¦
24 | 5 | Fonctionnalité 1 | 2022-03-18 | 2022-04-27 | [16 empty] | ¦
6 | 6 | Fonctionnalité 2 | 2022-03-30 | 2022-05-02 | [16 empty] | ¦
7 | 7 | Fonctionnalité 3 | 2022-04-20 | 2022-05-02 | [16 empty] | ¦
8 | 8 | Fonctionnalité 4 | 2022-05-03 | 2022-05-05 | [16 empty] | ¦
9 | 9 | Réalisation de l'écran principale de l'application | 2022-05-16 | 2022-05-16 | [16 empty] | ¦
19 | 10 | Réalisation de l'écran 1 de l'application | 2022-05-17 | 2022-06-16 | [16 empty] | ¦
20 | 11 | Réalisation de l'écran 2 de l'application | 2022-05-20 | 2022-06-04 | [16 empty] | ¦
12 | 12 | Réalisation de l'écran 3 de l'application | 2022-06-02 | 2022-06-04 | [16 empty] | ¦
13 | 13 | Document de spécification fonctionnel | 2022-05-23 | 2022-06-16 | [16 empty] | ¦
14 | 14 | Document de spécification technique | 2022-06-13 | 2022-06-16 | [16 empty] | ¦
15 | 15 | Réalisation du diagramme de GANTT | 2022-03-07 | 2022-06-16 | [16 empty] | ¦